## KANBAN
RockSat-C | KanBan Board
Who | To Do | Doing | Done | Date
Danielle |  |  | Built a gui with tabbed panes
Danielle |  |  | Constructed and showed graphs on Display.
Danielle |  |  | Created JFileChooser to simplify the Process of opening a file
Danielle |  | Interface Hayden’s code with the Interface in order to get data for graphs.
Danielle | Once data is allocated for graphs display it in graphs accordingly.
Hayden |  |  | Created project notes to roughly explain the classes used, logical flow, and equasions used to convert a raw data file in text format into data files containing graphical points. | March 08, 17 - March 15, 17
Hayden |  |  | Coded the first iterations of the classes documented in the project notes and tested them on several .txt files sent by Mickey. | March 08, 17 - March 15, 17
Hayden |  |  | Learn about how the MPU9250 and the ADXL377 units can be calibrated before data collection. | March 15, 17 - March 29, 17
Hayden |  |  | Learn how to translate the magnitude of each accelerometer axis back to its original axis using the gyroscope data. | March 15, 17 - March 29, 17
Hayden |  |  | Add the specific device ID to the data file's title so we know which accelerometer or gyroscope produced the data that created each file. | March 29, 17 - April 05, 17
Hayden |  |  | Modify the formulas used in the Calculator class to the formulas in the project notes. Essentially, refactored Calculator. | March 29, 17 - April 05, 17
Hayden |  |  | Met up with Mickey to collect fresh raw data files such as riding the elevator, going from one side of the hall to the other in the ET, and other controlled tests. | March 29, 17 - April 05, 17
Hayden |  |  | Apply the rotational matrices to re-orthogonalize the accelerations based on the gyroscope data. | March 29, 17 - April 12, 17
Hayden |  |  | Add the ability for the Calculator class to detect the offsets in the raw data and 'calibrate' each axis based on an average taken from the first several readings. | April 05, 17 - April 12, 17
Hayden |  |  | Created multiple graphs of data files generated by the back end using R-Studio to get a better understanding of what is being calculated. | April 05, 17 - April 12, 17
Hayden |  |  | Find a way to calibrate the data that doesn't cause drift inside the rotational matrices. (Fixed rotational matrix code) | April 12, 17 - April 19, 17
Hayden |  |  | Added some filtering to the acceleration values to ignore small changes and thus omit the noise. | April 12, 17 - April 19, 17
Hayden |  |  | Add the ability for the user to adjust the filtering values and the number of lines averaged when computing a flight. | April 19, 17 - May 03, 17
Hayden |  |  | Although it never ended up providing reliable readings of acceleration, Calculator now writes the ADXL377 unit's acceleration values to their own data files without doing any calculation with them. | May 03, 17 - May 10, 17
Hayden |  | Verify the results of the calculations done inside the Calculator class when converting from the raw flight file to data files. |  | March 29, 17 -
Hayden |  | Continue refactoring code and cut down the ever growing method of the Calculator class called calculateValues() |  | April 05, 17 -
Hayden |  | Start writing angle displacement data files to accompany the gyro's velocity data files already written. |  | April 26, 17 -
Hayden | Add Exception/Bug logging to the back end of the software.